## Sheet1
System Name: | Payroll Management System
Members: | Vaness Leonard C. Capuras
Jes Emmanuel Chavez
Kyla Dominic Genodiala
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Log-in | Vaness Leonard C. Capuras | 21/08/2024 | 2024-11-07 | Done
2. Sign up | Vaness Leonard C. Capuras | 2024-08-22 | 2024-11-07 | Done
3 Employee | Vaness Leonard C. Capuras | 2024-08-22 |  | Todo
4. Employee_terms | Vaness Leonard C. Capuras | 2024-08-23 |  | Todo
5. Job_title | Vaness Leonard C. Capuras | 2024-08-22 |  | Todo
6. Work_hours | Kyla Dominic Geniodala | 2024-08-23 |  | Todo
7. Salary_Payment | Kyla Dominic Geniodala | 2024-08-22 |  | Todo
8.Department | Jes Emmanuel Chavez | 2024-08-22 |  | Todo
9. Department_history | Jes Emmanuel Chavez | 2024-08-23 |  | Todo