## Sheet1
System Name: | Payroll Management System
Members: | Vaness Leonard C. Capuras
Jes Emmanuel Chavez
Kyla Dominic Genodiala
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Employee Management | Vaness Leonard C. Capuras | 21/08/2024 |  | Todo
1.1 Adding Employee | Vaness Leonard C. Capuras | 2024-08-22 |  | Todo
1.2 Display Employee UI | Vaness Leonard C. Capuras | 2024-08-22 |  | Todo
2. Payroll Calculation | Vaness Leonard C. Capuras | 2024-08-23 |  | Todo
2.1 Generate Report UI | Vaness Leonard C. Capuras | 2024-08-22 |  | Todo
3. Task Management | Kyla Dominic Geniodala | 2024-08-23 |  | Todo
4. Benefits Management | Kyla Dominic Geniodala | 2024-08-22 |  | Todo
5. Payroll Reporting | Jes Emmanuel Chavez | 2024-08-22 |  | Todo
6. User Management and Security | Jes Emmanuel Chavez | 2024-08-23 |  | Todo
6.1 Login User | Jes Emmanuel Chavez | 2024-08-22 |  | Todo
6.2 Logout User | Jes Emmanuel Chavez | 2024-08-22 |  | Todo